## Risk Register
Risk ID | Jira | Category | Risk statement | Evidence | Likelihood | Impact | Score | RAG | Proposed control | Testing layer
QR-001 | HELIX-1 | Specimen linkage | Specimen may not be correctly associated with its parent ServiceRequest. | Synthetic Patient, ServiceRequest and Specimen were created through the HAPI FHIR API. Retrieved resources did not visibly demonstrate a direct ServiceRequest-to-Specimen association. | 5 | 5 | 25 | HIGH | Validate FHIR references and workflow linkage through API testing and database validation before treating the relationship as confirmed. | API / SQL
QR-002 | HELIX-2 | Patient identification | Similar patient names may lead to selection of the wrong patient. | Exploratory testing identified multiple patient records when searching by the surname "Smith". | 4 | 5 | 20 | HIGH | Test patient-search disambiguation using additional identifiers and verify that the selected patient matches the intended record. | Manual / Playwright
QR-003 | HELIX-3 | Automation reliability | Cypress failures may reflect test or environment instability rather than product defects. | Project handover identifies intermittent CI failures and potential test-design weaknesses. | 5 | 4 | 20 | HIGH | Investigate flaky tests, isolate environment-related failures, improve test design and measure reliability before using the suite as dependable release evidence. | Cypress

## Scoring
Field | Convention | Explanation
Likelihood | 1–5 scale | 1 = unlikely; 5 = very likely
Impact | 1–5 scale | 1 = low impact; 5 = critical impact
Risk score | Likelihood × Impact | Higher scores indicate greater priority
RAG | Current classification | HIGH used for the three evidence-backed priority risks